## Project Plan
| PROJECT TITLE |  | START DATE
| Xây dựng Website bán khóa học làm nhạc |  | 2022-10-10 |  |  | PROJECT DURATION
| PROJECT MANAGER |  | END DATE |  |  | in days
| HOÀNG ĐỨC BÌNH |  | 2022-11-28 |  |  | 50
WBS NO. | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS
1 | Prepare for research | Complete |  | 2022-10-10 | 2022-10-20 | 11 |  | Not Started
1.1 | Chọn chủ đề | Complete | Hoàng Đức Bình | 2022-10-10 | 2022-10-10 | 1 |  | In Progress
1.2 | Tìm tài liệu về công nghệ đang sử dụng | In Progress | Hoàng Đức Bình | 2022-10-10 | 2022-10-14 | 5 |  | On Hold
1.3 | Tìm hiểu về công nghệ | In Progress | Hoàng Đức Bình | 2022-10-14 | 2022-10-16 | 3
1.3.1 | + Research object | Complete | Hoàng Đức Bình | 2022-10-16 | 2022-10-16 | 1
1.3.2 | + Research scope | Complete | Hoàng Đức Bình | 2022-10-17 | 2022-10-17 | 1
1.3.3 | + Define research goals | Complete | Hoàng Đức Bình | 2022-10-17 | 2022-10-17 | 1
1.3.4 | + Identify research questions | Complete | Hoàng Đức Bình | 2022-10-17 | 2022-10-17 | 1
1.3.5 | + Research Methods | Complete | Hoàng Đức Bình | 2022-10-18 | 2022-10-18 | 1
1.4 | - Research planning | Complete | Hoàng Đức Bình | 2022-10-18 | 2022-10-20 | 3
2 | Research Deployment | Complete |  | 2022-10-21 | 2022-11-26 | 37
2.1 | Thiết kế giao diện | Complete | Hoàng Đức Bình | 2022-10-21 | 2022-10-30 | 10
2.2 | - Hỗ trợ thiết kế giao diện và thiết kế database | Complete | Hoàng Đức Bình | 2022-10-21 | 2022-10-30 | 10
2.2.1 | Thử nghiệm code xử lý | Complete | Hoàng Đức Bình | 2022-10-21 | 2022-11-26 | 37
2.2.2 | Hoàn tất giao diện | Complete | Hoàng Đức Bình | 2022-11-21 | 2022-11-25 | 5
2.2.3 | Code thực thi các chức năng cho phần mềm | Complete | Hoàng Đức Bình | 2022-10-30 | 2022-11-25 | 27
2.2.4 | + Check lỗi | Complete | Hoàng Đức Bình | 2022-10-30 | 2022-11-25 | 27
2.3 | + Check data | Complete | Hoàng Đức Bình | 2022-10-25 | 2022-10-30 | 6
3 | Write a research report | In Progress |  | 2022-11-23 | 2022-11-27 | 5
3.1 | - Chapter 1: Introduction | Complete | Hoàng Đức Bình | 2022-11-23 | 2022-11-27 | 5
3.2 | - Chapter 2: Literature Review | Complete | Hoàng Đức Bình | 2022-11-23 | 2022-11-27 | 5
3.3 | - Chapter 3: Methodology | Complete | Hoàng Đức Bình | 2022-11-24 | 2022-11-27 | 4
3.4 | - Chapter 4: Data analysis | Complete | Hoàng Đức Bình | 2022-11-24 | 2022-11-27 | 4
3.5 | - Chapter 5: Project plan | In Progress | Hoàng Đức Bình | 2022-11-24 | 2022-11-27 | 4
3.6 | - Chapter 6,7: Discussion, Conclusion | In Progress | Hoàng Đức Bình | 2022-11-25 | 2022-11-27 | 3
3.7 | - Table of contents and research report format | Complete | Hoàng Đức Bình | 2022-11-25 | 2022-11-27 | 3
4 | Research presentation | In Progress |  | 2022-11-27 | 2022-11-28 | 2
4.1 | – Build report slides | Complete | Hoàng Đức Bình | 2022-11-27 | 2022-11-27 | 1
4.2 | – Report presentation | In Progress | Hoàng Đức Bình | 2022-11-27 | 2022-11-28 | 2

## Data
Hoàng Đức Bình

## Project Plan Template
| PROJECT TITLE |  | START DATE
|  |  | 2021-07-01 |  |  | PROJECT DURATION
| PROJECT MANAGER |  | END DATE |  |  | in days
|  |  | 2021-09-11 |  |  | 73
WBS NO. | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS
1 | Chuẩn bị cho nghiên cứu | Complete |  | 2021-07-01 | 2021-07-15 | 15 |  | Not Started
1.1 | - Chọn đề tài | Complete |  | 2021-07-01 | 2021-07-03 | 3 |  | In Progress
1.2 | - Thu thập tài liệu | Complete |  | 2021-07-04 | 2021-07-08 | 5 |  | On Hold
1.3 | - Xác định các yêu cầu của đề tài | Complete |  | 2021-07-09 | 2021-07-13 | 5
1.3.1 | +Đối tượng nghiên cứu | Complete |  | 2021-07-09 | 2021-07-09 | 1
1.3.2 | +Phạm vi nghiên cứu | Complete |  | 2021-07-10 | 2021-07-10 | 1
1.3.3 | + Xác định mục tiêu nghiên cứu | Complete |  | 2021-07-11 | 2021-07-11 | 1
1.3.4 | + Xác định câu hỏi nghiên cứu | Complete |  | 2021-07-12 | 2021-07-12 | 1
1.3.5 | + Phương pháp nghiên cứu | Complete |  | 2021-07-13 | 2021-07-13 | 1
1.4 | - Lập kế hoạch | Complete |  | 2021-07-14 | 2021-07-15 | 2
2 | Triển khai nghiên cứu | Complete |  | 2021-07-16 | 2021-08-20 | 36
2.1 | -Đọc các bài báo nghiên cứu liên quan | Complete |  | 2021-07-16 | 2021-07-20 | 5
2.2 | -Thu thập và xử lý dữ liệu | Complete |  | 2021-07-21 | 2021-08-20 | 31
2.2.1 | +Xây dựng bộ câu hỏi khảo sát | Complete |  | 2021-07-21 | 2021-07-28 | 8
2.2.2 | +Tạo bộ câu hỏi nghiên cứu bằng google form | Complete |  | 2021-07-29 | 2021-08-02 | 5
2.2.3 | +Gửi và nhận các thông tin khảo sát | Complete |  | 2021-08-03 | 2021-08-10 | 8
2.2.4 | +Xử lý dữ liệu | Complete |  | 2021-08-11 | 2021-08-17 | 7
2.3 | +Kiểm chứng kết quả nghiên cứu | Complete |  | 2021-08-18 | 2021-08-20 | 3
3 | Viết báo cáo nghiên cứu | In Progress |  | 2021-08-21 | 2021-09-11 | 22
3.1 | - Chapter 1: Introduction | Complete |  | 2021-08-21 | 2021-08-23 | 3
3.2 | - Chapter 2: Literature Review | Complete |  | 2021-08-24 | 2021-08-27 | 4
3.3 | - Chapter 3: Methodology | Complete |  | 2021-08-28 | 2021-08-30 | 3
3.4 | - Chapter 4: Data analysis | Complete |  | 2021-09-01 | 2021-09-07 | 7
3.5 | - Chapter 5: Discussion | On Hold |  | 2021-09-08 | 2021-09-10 | 3
3.6 | - Chapter 6: Conclusion | On Hold |  | 2021-09-11 | 2021-09-11 | 1
3.7 | - Mục lục và định dạng báo cáo nghiên cứu | Complete |  | 2021-09-08 | 2021-09-09 | 2
4 | Trình bày nghiên cứu | In Progress |  | 2021-09-08 | 2021-09-11 | 4
4.1 | – Xây dựng slide báo cáo | Complete |  | 2021-09-08 | 2021-09-10 | 3
4.2 | – Trình bày báo cáo | On Hold |  | 2021-09-11 | 2021-09-11 | 1

## BLANK - Project Plan Template
PROJECT PLAN TEMPLATE
| PROJECT TITLE |  | START DATE
PROJECT DURATION
| PROJECT MANAGER |  |  |  |  | in days
1
WBS NO. | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS
1 | PROJECT CONCEPTION AND INITIATION |  |  |  |  | 1 |  | Not Started
1.1 | – Project Charter |  |  |  |  | 1 |  | In Progress
1.1.1 | –– Project Charter Revisions |  |  |  |  | 1 |  | Complete
1.2 | – Research |  |  |  |  | 1 |  | On Hold
1.3 | – Projections |  |  |  |  | 1
1.4 | – Stakeholders |  |  |  |  | 1
1.5 | – Guidelines |  |  |  |  | 1
1.6 | – Project Initiation |  |  |  |  | 1
2 | PROJECT DEFINITION AND PLANNING |  |  |  |  | 1
2.1 | – Scope & Goal Setting |  |  |  |  | 1
2.2 | – Budget |  |  |  |  | 1
2.3 | – Communication Plan |  |  |  |  | 1
2.4 | – Risk Management |  |  |  |  | 1
3 | PROJECT LAUNCH & EXECUTION |  |  |  |  | 1
3.1 | – Status & Tracking |  |  |  |  | 1
3.2 | – KPIs |  |  |  |  | 1
3.2.1 | –– Monitoring |  |  |  |  | 1
3.2.2 | –– Forecasts |  |  |  |  | 1
3.3 | – Project Updates |  |  |  |  | 1
3.3.1 | –– Chart Updates |  |  |  |  | 1
4 | PROJECT PERFORMANCE / MONITORING |  |  |  |  | 1
4.1 | – Project Objectives |  |  |  |  | 1
4.2 | – Quality Deliverables |  |  |  |  | 1
4.3 | – Effort & Cost Tracking |  |  |  |  | 1
4.4 | – Project Performance |  |  |  |  | 1
Double-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.